## 060926
Open Order as of 06/09/2026
PO# | SKUNumber | Product | Qty | MFG Status | Label Status | Bottle Status | Bulk Test Status | Bottle Test Status | Target Ship Date | Comments | Pallet count | Est weight | Est Case Weight | Est Bottle Weight
NS20251111 | NA-GW-014 | IronAxis 30ct | 7500 | Complete | label shipped | In process | Complete |  | TBD |  | 3 | 1095 | 1.5 lb | 0.10 lb
NS20251111 | NA-SS-013 | AdrenalAxis 30ct | 7500 | Complete | label shipped | In process | Complete |  | TBD |  | 3 | 1050 | 1.75 lb | 0.13 lb
NS20251111 | NA-GW-007 | MultiAxis 30ct | 15000 | Complete | label shipped | Scheduled 06/12/26 | Complrete |  | TBD |  | 6 | 2160 | 1.5 lb | 0.10 lb
NS20251111 | NA-IF-015 | ResolvAxis 30ct | 7500 | Complete | label shipped | Scheduled 06/15/26 | Complete |  | TBD |  | 3 | 1400 | 1.5 lb | 0.10 lb
NS20251111 | NA-LV-010 | MitoAxis 30ct | 10000 | Complete | label shipped | Scheduled; ETA 06/19 | In process |  | TBD | TMLA fully executed and returned to Kaneka | 4 | 1445 | 1.25 lb | 0.09 lb
NS20251111 | NA-HR-009 | DIMAxis 60ct | 15000 | In process | label shipped | Scheduled; ETA 06/19 | In process |  | TBD |  | 6 | 4050 | 3.25 lb | 0.25 lb
NS20251111 | NA-GW-011 | OmegaAxis 60ct | 10000 | In process | label shipped | Scheduled; ETA 06/19 | In process |  | TBD |  | 4 | 2690 | 3 lb | 0.23 lb
NS20251111 | NA-LV-012 | Longevity 60ct | 7500 | pending RM for benchtop |  |  |  |  | TBD |  | 3 | 2200